# Project Plan

Deliver an AI-based BRD generation platform that captures user project details, extracts uploaded document content, orchestrates specialized LLM agents, validates BRD quality, supports review/edit/regeneration, exports DOCX/PDF, and maintains generation history with privacy and security controls.

Methodology: Hybrid

Total Duration: 4 months

# Team Structure

| Role | Count | Responsibilities |
| --- | --- | --- |
| Project Manager | 1 | Plan delivery, manage scope, timeline, risks, reporting, and stakeholder coordination. |
| Product Owner | 1 | Own backlog, acceptance criteria, prioritization, and business validation. |
| UX/UI Designer | 1 | Design guided input forms, review/edit screens, history views, and export flows. |
| Full Stack Engineers | 3 | Build frontend, backend APIs, document handling, editor, export, history, and persistence features. |
| AI/LLM Engineer | 1 | Design prompts, agent orchestration, source traceability, hallucination controls, and generation performance. |
| QA Engineer | 1 | Create and execute functional, integration, regression, performance, and acceptance tests. |
| DevOps/Security Engineer | 1 | Set up environments, CI/CD, monitoring, secure storage, access controls, and privacy/security checks. |

# Project Phases

## Phase 1 — Discovery, Architecture, and UX Design

Duration: 2 weeks | Weeks 1–2

Objectives:

Confirm detailed scope and acceptance approach.

Define secure platform architecture and AI workflow.

Create UX designs for core user journeys.

Tasks:

| Task ID | Task Name | Role | Days | Linked Requirements |
| --- | --- | --- | --- | --- |
| T-001 | Confirm backlog, acceptance criteria, and release priorities | Product Owner | 3 | FR-001, FR-002, FR-003, FR-004, FR-005, FR-006, FR-007, FR-008, FR-009 |
| T-002 | Define solution architecture, data model, storage, and API boundaries | Full Stack Engineers | 5 | FR-001, FR-002, FR-006, FR-009 |
| T-003 | Design LLM agent orchestration, prompt strategy, and output schema | AI/LLM Engineer | 5 | FR-003, FR-004, FR-005, FR-007 |
| T-004 | Create UX wireframes for input, upload, generation, edit, regenerate, export, and history | UX/UI Designer | 5 | FR-001, FR-002, FR-006, FR-007, FR-008, FR-009 |
| T-005 | Define privacy, retention, audit, and secure processing controls | DevOps/Security Engineer | 4 | FR-001, FR-002, FR-006, FR-008, FR-009 |

Deliverables:

Approved product backlog

Architecture and AI workflow design

UX wireframes

Security and privacy control plan

## Phase 2 — Core Platform and MVP Generation Build

Duration: 6 weeks | Weeks 3–8

Objectives:

Build secure core application foundation.

Implement project detail capture and document extraction.

Generate structured BRD drafts with required sections.

Tasks:

| Task ID | Task Name | Role | Days | Linked Requirements |
| --- | --- | --- | --- | --- |
| T-006 | Build guided project detail capture with validation for required inputs and long text | Full Stack Engineers | 8 | FR-001 |
| T-007 | Implement PDF, DOCX, and TXT upload, extraction, status feedback, and secure file handling | Full Stack Engineers | 10 | FR-002 |
| T-008 | Build base BRD generation service for all required sections and 10-minute target | AI/LLM Engineer | 12 | FR-003 |
| T-009 | Implement persistence for generated BRD drafts and section-level content | Full Stack Engineers | 8 | FR-006, FR-009 |
| T-010 | Create MVP integration tests for input, upload, extraction, generation, and saving | QA Engineer | 7 | FR-001, FR-002, FR-003, FR-006 |

Deliverables:

Working MVP application

Document extraction service

Base AI BRD generation service

MVP test results

## Phase 3 — Agent Orchestration, Quality Controls, Editing, and Export

Duration: 4 weeks | Weeks 9–12

Objectives:

Implement specialized agents and consistent final BRD assembly.

Enable user review, editing, regeneration, export, and quality validation.

Add history and duplication capability.

Tasks:

| Task ID | Task Name | Role | Days | Linked Requirements |
| --- | --- | --- | --- | --- |
| T-011 | Implement specialized agents for project plan, effort estimation, functional requirements, and non-functional requirements | AI/LLM Engineer | 8 | FR-004 |
| T-012 | Build requirement quality validation for unique IDs, SMART wording, priorities, and acceptance criteria | AI/LLM Engineer | 6 | FR-005 |
| T-013 | Build section-level review, edit, save, audit trail, and selective regeneration | Full Stack Engineers | 10 | FR-006, FR-007 |
| T-014 | Implement DOCX and PDF export preserving structure and excluding hidden metadata | Full Stack Engineers | 7 | FR-008 |
| T-015 | Build generation history with search by date/project name and duplicate-to-new-version | Full Stack Engineers | 7 | FR-009 |

Deliverables:

Agent orchestration module

Requirement validation engine

Editable BRD workspace

Selective regeneration capability

DOCX/PDF export

Generation history

## Phase 4 — Hardening, UAT, Compliance Validation, and Launch

Duration: 4 weeks | Weeks 13–16

Objectives:

Validate functional completeness, performance, quality, and security.

Complete UAT against business objectives.

Prepare production launch and operational support.

Tasks:

| Task ID | Task Name | Role | Days | Linked Requirements |
| --- | --- | --- | --- | --- |
| T-016 | Execute full system, regression, and acceptance testing across all workflows | QA Engineer | 8 | FR-001, FR-002, FR-003, FR-004, FR-005, FR-006, FR-007, FR-008, FR-009 |
| T-017 | Run performance testing for generation completion within 10 minutes for standard inputs | QA Engineer | 5 | FR-003 |
| T-018 | Perform security, privacy, retention, auditability, and metadata exposure validation | DevOps/Security Engineer | 6 | FR-001, FR-002, FR-006, FR-008, FR-009 |
| T-019 | Conduct UAT and validate business targets for speed, completeness, and reduced analyst dependency | Product Owner | 7 | FR-003, FR-005, FR-006, FR-008 |
| T-020 | Prepare production deployment, monitoring, rollback plan, and user enablement materials | DevOps/Security Engineer | 5 | FR-001, FR-002, FR-003, FR-006, FR-008, FR-009 |

Deliverables:

Test completion report

Performance validation report

Security and privacy validation report

UAT sign-off

Production release package

User guide

# Risk Register

| ID | Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-001 | LLM outputs may contain hallucinations, inconsistent structure, or unsupported claims. | Medium | High | Use controlled prompts, structured output schemas, source traceability, validation checks, and human review before export. | AI/LLM Engineer |
| R-002 | Document extraction quality may vary across uploaded PDFs and DOCX files. | Medium | Medium | Use proven extraction libraries, provide extraction status feedback, handle unreadable content gracefully, and include sample file test coverage. | Full Stack Engineers |
| R-003 | Privacy or retention gaps may expose uploaded or generated content beyond policy limits. | Low | High | Implement secure storage, access controls, audit logs, retention/deletion rules, and security review before launch. | DevOps/Security Engineer |

# Definition of Done

All Must Have requirements FR-001 through FR-006 and FR-008 meet approved acceptance criteria.

Should Have requirements FR-007 and FR-009 are delivered or formally accepted for release deferral.

Generated BRD includes all required sections in the configured structure.

Standard BRD generation completes within 10 minutes for at least 90% of tested submissions.

Requirement quality checks flag missing measurable criteria and enforce unique IDs.

Users can review, edit, save, selectively regenerate, export, and retrieve BRDs.

DOCX and PDF exports preserve headings, lists, tables, and section order.

Privacy, retention, secure upload handling, auditability, and metadata exclusion controls are validated.

Regression, integration, performance, and UAT testing are completed with no open critical defects.

Production deployment, monitoring, rollback plan, and user enablement materials are complete.