# Project Plan

12-month phased delivery of an AI-powered personal finance advisor application targeting young professionals. The project employs Agile methodology with iterative releases, starting with core expense analysis capabilities, followed by AI recommendation engines, and concluding with advanced features. Each phase delivers working software with increasing sophistication in financial insights and user engagement.

Methodology: Agile

Total Duration: 12 months

# Team Structure

| Role | Count | Responsibilities |
| --- | --- | --- |
| Product Owner | 1 | Stakeholder management, backlog prioritization, acceptance criteria validation, regulatory compliance oversight |
| Scrum Master | 1 | Sprint planning, team facilitation, impediment removal, process optimization, velocity tracking |
| ML Engineer | 2 | AI model development, expense categorization algorithms, recommendation engines, model training and optimization |
| Backend Developer | 3 | API development, data processing pipelines, security implementation, database design, integration services |
| Frontend Developer | 2 | Responsive UI development, dashboard visualizations, user experience implementation, chatbot interface |
| QA Engineer | 2 | Test automation, security testing, accuracy validation, performance testing, compliance verification |
| DevOps Engineer | 1 | Infrastructure setup, CI/CD pipelines, monitoring, deployment automation, security hardening |
| UI/UX Designer | 1 | User research, wireframing, visual design, usability testing, design system maintenance |

# Project Phases

## Phase 1 — Foundation & Core Processing

Duration: 12 weeks | Weeks 1–12

Objectives:

Establish secure infrastructure with PCI DSS compliance

Implement bank statement upload and data extraction

Develop basic expense categorization ML model

Create foundational user authentication and data security

Tasks:

| Task ID | Task Name | Role | Days | Linked Requirements |
| --- | --- | --- | --- | --- |
| T-001 | Infrastructure setup with security hardening and compliance frameworks | DevOps Engineer | 10 | FR-001 |
| T-002 | Secure file upload service with PDF/CSV parsing engine | Backend Developer | 15 | FR-001 |
| T-003 | ML model for expense categorization with training dataset preparation | ML Engineer | 20 | FR-002 |
| T-004 | User authentication system with role-based access control | Backend Developer | 12 | FR-001 |
| T-005 | Basic responsive UI for upload and transaction review | Frontend Developer | 15 | FR-001, FR-002 |

Deliverables:

Production-ready infrastructure with PCI DSS compliance

Secure bank statement upload functionality

Expense categorization engine with 90% accuracy

User authentication and data encryption system

## Phase 2 — AI Intelligence & Dashboard

Duration: 12 weeks | Weeks 13–24

Objectives:

Develop personalized savings recommendation engine

Build interactive financial dashboard with visualizations

Implement user feedback loop for ML model refinement

Create spending pattern analysis algorithms

Tasks:

| Task ID | Task Name | Role | Days | Linked Requirements |
| --- | --- | --- | --- | --- |
| T-006 | Savings recommendation AI engine with pattern detection | ML Engineer | 18 | FR-003 |
| T-007 | Interactive dashboard with charts and trend visualization | Frontend Developer | 20 | FR-006 |
| T-008 | User feedback mechanism for transaction reclassification | Backend Developer | 10 | FR-002 |
| T-009 | Analytics engine for spending trends and insights | Backend Developer | 15 | FR-006 |
| T-010 | Performance optimization and load testing | DevOps Engineer | 12 | FR-001, FR-006 |

Deliverables:

AI-powered savings recommendations with 3+ actionable tips

Comprehensive financial dashboard with expense breakdown

User feedback system improving model accuracy

Performance benchmarks meeting sub-30-second processing

## Phase 3 — Investment & Goal Management

Duration: 12 weeks | Weeks 25–36

Objectives:

Implement investment advice engine with risk profiling

Develop goal-setting and tracking functionality

Create insurance recommendation system

Ensure SEC and financial advisory compliance

Tasks:

| Task ID | Task Name | Role | Days | Linked Requirements |
| --- | --- | --- | --- | --- |
| T-011 | Risk assessment questionnaire and profiling algorithm | ML Engineer | 15 | FR-004 |
| T-012 | Investment recommendation engine with portfolio suggestions | ML Engineer | 20 | FR-004 |
| T-013 | Goal creation and tracking system with progress visualization | Backend Developer | 12 | FR-007 |
| T-014 | Insurance recommendation module with product comparisons | Backend Developer | 15 | FR-005 |
| T-015 | Compliance review and legal disclaimer implementation | Product Owner | 10 | FR-004, FR-005 |

Deliverables:

Investment advice engine with risk-aligned recommendations

Goal-setting interface with milestone tracking

Insurance product recommendation system

SEC-compliant disclosures and legal framework

## Phase 4 — AI Chatbot & Optimization

Duration: 12 weeks | Weeks 37–48

Objectives:

Deploy conversational AI chatbot for financial Q&A

Optimize all ML models based on user feedback and usage data

Enhance platform performance and scalability

Execute comprehensive user acceptance testing and launch prep

Tasks:

| Task ID | Task Name | Role | Days | Linked Requirements |
| --- | --- | --- | --- | --- |
| T-016 | NLP chatbot development with financial knowledge base | ML Engineer | 25 | FR-008 |
| T-017 | Chatbot UI integration with context-aware responses | Frontend Developer | 12 | FR-008 |
| T-018 | ML model retraining with production data and accuracy improvements | ML Engineer | 15 | FR-002, FR-003 |
| T-019 | End-to-end UAT with target user segment | QA Engineer | 20 | FR-001, FR-002, FR-003, FR-004, FR-006, FR-007, FR-008 |
| T-020 | Production launch preparation and marketing readiness | Product Owner | 10 | FR-001, FR-002, FR-003, FR-004, FR-005, FR-006, FR-007, FR-008 |

Deliverables:

24/7 AI chatbot with 90% accuracy on financial queries

Optimized ML models with enhanced personalization

Production-ready platform passing all UAT criteria

Launch strategy and user onboarding materials

# Risk Register

| ID | Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-001 | ML model accuracy falls below 90% threshold affecting user trust and recommendation quality | Medium | High | Implement continuous model monitoring with automated retraining pipeline. Maintain diverse training dataset with regular updates. Establish user feedback loop for model corrections. Plan for manual review process for edge cases. | ML Engineer Lead |
| R-002 | Regulatory compliance gaps in financial advisory or data privacy leading to legal exposure | Medium | High | Engage legal counsel for SEC and GDPR compliance review at each phase. Implement comprehensive audit logging. Include prominent disclaimers for all investment advice. Conduct third-party security audit before launch. Obtain necessary financial advisory licenses. | Product Owner |
| R-003 | User adoption falls short of 10K target within 6 months due to trust concerns or competition | Medium | Medium | Launch aggressive pre-release marketing campaign targeting young professionals. Implement referral incentives and early adopter programs. Emphasize security and privacy features in messaging. Partner with financial influencers for credibility. Offer free trial period with premium features. | Product Owner |

# Definition of Done

All acceptance criteria met and validated by Product Owner

Code reviewed and approved by at least one peer developer

Unit test coverage minimum 80% with all tests passing

Integration tests completed successfully in staging environment

Security scan completed with no critical or high vulnerabilities

Performance benchmarks met per requirement specifications

User documentation and help content updated

Compliance requirements validated where applicable

QA sign-off obtained with no blocking defects

Deployed to production and verified operational